## Main
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
Database Management | 6 | 3 | 1 | 1 | [5 empty] | 5
Basic Product User Interface | 3 | 1 | 2 | [6 empty] | 3
Basic Product User Authentication | 2 | 0 | 2 | [6 empty] | 2
Refined Product User Interface | 5 | 0 | 1 | [6 empty] | 1
Refined Product User Authentication | 2 | 0 | 0 | [6 empty] | 0
Basic Class Information Displayed | 2 | 0 | 0 | [6 empty] | 0
Detailed Class Information Displayed | 2 | 0 | 0 | [6 empty] | 0
Sorting and Searching Classes? | 0 | 0 | 0 | [6 empty] | 0
Ability to design a "Plan of Study" | 0 | 0 | 0 | [6 empty] | 0
Ability to save "Plan of Study" | 0 | 0 | 0 | [6 empty] | 0
Actual Remaining Effort | 22 | 18 | 12 | 11 | 11 | 11 | 11 | 11 | 11
Estimated Remaining Effort | 22 | 19.25 | 16.5 | 13.75 | 11 | 8.25 | 5.5 | 2.75 | 0

## Details
Completion
Database Management |  | 6pts
| Create Tables | 2pts | S1
| Data Entry | 3pts | S1 (Partial), S2(Remainder)
| Make Improvements/Additions? | 1pts
Basic Product User Interface |  | 3pts
| Concept Design | 1pts | S1
| Create Basic Login Window | 1pts | S1.5
| Create Basic Main Window | 1pts | S1.5
Basic Product User Authentication |  | 2pts
| Design Basic UA Logic | 1pts | S1.5
| Code Logic | 1pts | S1.5
Refined Product User Interface |  | 5pts
| Add Tabs to Main Window | 1pts | S1.5
| Complete Designs for Other Tabs | 1pts
| Design Product Theme | 1pts
| Update Product with Unifed Theme | 2pts
Refined Product User Authentication |  | 2pts?
| Improve Basic UA Logic (If Possible) | 1pts?
| Add Functionality to change Password | 1pts
Basic Class Information Displayed |  | 2pts
| Display Class/Paper Internal Code | 1pts
| Display Class/Paper Name | 1pts
Detailed Class Information Displayed |  | 2pts
| Display Class/Paper Semester | 1pts
| Display Class/Paper Year | 1pts
Sorting and Searching Classes
Ability to design a "Plan of Study"
Ability to save "Plan of Study"